## Sheet1
Task | Start Hours | Hours Spent Day5 | Hours Spent Day4 | Hours Spent Day3 | Hours Spent Day2 | Hours Spent Day1 | Total Hours
Get Doc Registration Form | 2 | 2 | 0 | 0 | 0 | 0 | 2
Design Doctor Class | 6 | 2 | 1 | 1 | 1 | 1 | 6
Design Data Store | 2 | 2 | 0 | 0 | 0 | 0 | 2
Build Data Store | 2 | 0 | 0 | 0 | 2 | 0 | 2
Implement Doctor Class | 2 | 0 | 0 | 0 | 2 | 0 | 2
Test Data Store | 2 | 0 | 0 | 0 | 2 | 0 | 2
Design UI (Prototype) | 8 | 2 | 2 | 2 | 1 | 1 | 8
Design Test Case | 8 | 2 | 2 | 2 | 1 | 1 | 8
Unit Test Doctor Class | 4 | 0 | 0 | 0 | 2 | 2 | 4
Actual Remaining Hours | 36 | 26 | 21 | 16 | 5 | 0
Estimated Remaining Hours | 36 | 28.8 | 21.6 | 14.4 | 7.2 | 0