## Sheet1
Task | Start Hours | Hours Spent Day10 | Hours Spent Day9 | Hours Spent Day8 | Hours Spent Day7 | Hours Spent Day6 | Hours Spent Day5 | Hours Spent Day4 | Hours Spent Day3 | Hours Spent Day2 | Hours Spent Day1 | Total Hours
Get Doc Registration Form | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Design Doctor Class | 6 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6
Design Data Store | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Build Data Store | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Implement Doctor Class | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Test Data Store | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Design UI (Prototype) | 8 | 6 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Design Test Case | 8 | 6 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Unit Test Doctor Class | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4
Get Patient Registration Form | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2
Design Patient Class | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 3
Implement Patient Class | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 2
Design Test Case | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 3 | 2 | 1 | 0 | 6
Unit Test Patient Class | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 4
Design UI (Prototype) | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 4
Design Data Store | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2
Build Data Store | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2
Test Data Store | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2
Actual Remaining Hours | 63 | 53 | 48 | 43 | 32 | 27 | 15 | 11 | 8 | 5 | 0
Estimated Remaining Hours | 63 | 56.7 | 50.4 | 44.1 | 37.8 | 31.5 | 25.2 | 18.9 | 12.6 | 6.3 | 0